## gantt
ID | Task Name | Duration | Assigned | W1 (Feb 25) | W2 (Mar 4) | W3 (Mar 11) | W4 (Mar 18) | W5 (Mar 25) | W6 (Apr 1) | W7 (Apr 8) | W8 (Apr 15) | W9 (Apr 22) | W10 (Apr 29) | W11 (May 6)
Spring Break (Mar 6-15) --- No Work
1 | Env Setup & Scaffolding | 1 week | C&Y | C&Y
1.1 | CMake Build Configuration | 2 days | C&Y | C&Y
1.2 | BFSimulateCmd Skeleton | 2 days | C&Y | C&Y
1.3 | MEL Round-Trip Verification | 1 day | C&Y | C&Y
2 | Skeleton Rig & Maneuvering Fns | 2 weeks | Y |  | Y* |  | Y | Y
2.1 | BFState Struct & Joint Enum | 2 days | Y |  | Y*
2.2 | Maneuvering Function (Eqs. 1-3) | 3 days | Y |  |  |  | Y
2.3 | Joint-Rotation Applicator | 2 days | Y |  |  |  | Y
2.4 | Visual Verification | 3 days | Y |  |  |  |  | Y
3 | Aerodynamic Force Model | 1.5 weeks | C |  | C* |  | C | C
3.1 | Wing-Panel Normal Computation | 2 days | C |  | C*
3.2 | Lift/Drag Polynomial Eval (Eqs. 4-6) | 3 days | C |  |  |  | C
3.3 | Newton Integration | 3 days | C |  |  |  | C | C
4 | Curl-Noise Vortex Force | 1 week | C |  |  |  |  | C | C
4.1 | 3-D Gradient Perlin Noise | 2 days | C |  |  |  |  | C
4.2 | Finite-Difference Curl (Eq. 7) | 2 days | C |  |  |  |  | C
4.3 | UI Integration | 1 day | C | [5 empty] | C
5 | Maneuver Control & Decoupling | 1.5 weeks | Y |  |  |  |  | Y | Y
5.1 | Preferred Acceleration (Eq. 8) | 3 days | Y |  |  |  |  | Y
5.2 | Local Accel Decoupling (Eqs. 10-11) | 2 days | Y |  |  |  |  | Y
5.3 | Sliding-Window Smoother (Eq. 12) | 3 days | Y | [5 empty] | Y
6 | MEL/Python UI Panel | 1 week | C | [5 empty] | C
6.1 | Full Control Layout | 2 days | C | [5 empty] | C
6.2 | Callbacks | 1 day | C | [5 empty] | C
6.3 | Command Invocation & Bake | 2 days | C | [5 empty] | C
7 | Alpha Demo Integration | 0.5 weeks | C&Y | [5 empty] | C&Y | *1
7.1 | End-to-End Integration Test | 1 day | C&Y | [5 empty] | C&Y
7.2 | Integration Bug Fixes | 1 day | C&Y | [5 empty] | C&Y
7.3 | Alpha Scene Packaging | 1 day | C&Y | [5 empty] | C&Y
8 | Swarm Simulation & Aggregation | 1.5 weeks | Y | [6 empty] | Y | Y
8.1 | Multi-Agent State Management | 2 days | Y | [6 empty] | Y
8.2 | Centroid-Based Preferred Accel | 3 days | Y | [6 empty] | Y
8.3 | Swarm UI & Demo Scene | 3 days | Y | [7 empty] | Y
9 | Export & Beta Integration | 0.5 weeks | C | [6 empty] | C | *2
9.1 | Export Cache Button | 1 day | C | [6 empty] | C
9.2 | Wind Parameter Round-Trip | 1 day | C | [6 empty] | C
9.3 | Beta Scene Packaging & Tag | 1 day | C | [6 empty] | C
10 | Testing & Final Demo | 1 week | C&Y | [7 empty] | C&Y | C&Y | *3
10.1 | Regression Testing | 2 days | C&Y | [7 empty] | C&Y
10.2 | Swarm Performance Profiling | 2 days | C&Y | [8 empty] | C&Y
10.3 | Quick-Start PDF & Code Submission | 1 day | C&Y | [9 empty] | C&Y
*1 = Alpha version release (~Apr 8)
*2 = Beta version release (Apr 15)
*3 = Final Demo (May 5) / Code Due (May 11)
C = Cecilia Chen ¦ Y = Yiding Tian ¦ C&Y = Both
* = Partial week --- both unavailable from Mar 6 (Spring Break)